## RDM Service PMS of 2 MVA Port
2026-09-15 12:27
MAHESHWARI DISTRIBUTORS PROJECT TITLE : RDM Service PMS of 2 MVA Portal Substation PO NUMBER : 5100033887 DATA ENTRY OPERATOR : Mahender Kumar Gurjar |  |  |  | Owner : DK Shriwal :- 8233330578 VRE : Aarti Bala :- 8824133320 Site Incharge: : Dinesh Purohit :- 8003698657 Process Coordinator : Tulsi Sen :- 9875789834
|  |  |  | Start Date |  | 2026-06-02 |  | End Date | 2026-08-20
|  |  |  | RDM Service PMS of 2 MVA Portal Substation | [14 empty] | WEEK 1 |  |  |  | WEEK 2 |  |  |  | WEEK 3 |  |  |  | WEEK 4 |  |  |  | WEEK 5 |  |  |  | WEEK 6 |  |  |  | WEEK 7 |  |  |  | WEEK 8 |  |  |  | WEEK 9 |  |  |  | WEEK 10 |  |  |  | WEEK 11 |  |  |  | WEEK 12 |  |  |  | WEEK 13 |  |  |  | WEEK 14 |  |  |  | WEEK 15 |  |  |  | WEEK 16 |  |  |  | WEEK 17 |  |  |  | WEEK 18 |  |  |  | WEEK 19 |  |  |  | WEEK 20 |  |  |  | WEEK 21 |  |  |  | WEEK 22 |  |  |  | WEEK 23
[7 empty] | PLAN |  |  | ACTUAL | time axis 2026-06-02 to 2026-09-14
Unique I.d. | WBS NUMBER | TASK TITLE | Qty | UOM | WORK OWNER / INCHARGE | MAN POWER | START DATE | END DATE | DURATION | PLANNED | ACTUAL | STATUS | TIME DELAY | Total | NO. Completed | PCT OF TASK COMPLETE | COMPLETE | Remark | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon | Tue | Wed | Thu | Fri | Sat | Mon
FALSE
RDMS00001 | A | 2 MVA Portal Substation at RD Mines-Description of Work | [16 empty] | 2026-06-02: FALSE
RDMS00002 | 1 | Shifting, Erection & commissioning of 2MVA 11KV/0.433KV Conventional substation and as per BOQ attached. All tools, tackles , hydra, trucks shall be in vendor sope. | [16 empty] | 2026-06-02: FALSE
RDMS00003 | 1 a | Civil building readiness for equipment erection work | 1 | LS | Dinesh Purohit | 10 | 2026-07-10 | 2026-10-05 | 35 | 2026-10-05 |  |  | 2088:00 | 1 |  | 70% |  |  | 2026-06-02: #REF!
RDMS00004 | 1 b | Finishing work of civil building | 1 | LS | Dinesh Purohit | 10 | 2026-07-10 | 2026-10-10 | 40 | 2026-10-10 |  |  | 2208:00 | 1 |  | 0% |  |  | 2026-06-02: #REF!
RDMS00005 | 2 | Cable Schedule | [16 empty] | 2026-06-02: FALSE
RDMS00006 | 2A | 11kv PORTAL S/S | [16 empty] | 2026-06-02: FALSE
RDMS00007 | 1 | 11kv BBL S/S to Portal S/S I/C = 3cx300sqmm AL. | 485 | Mtr | Dinesh Purohit | 10 | 2026-09-07 | 2026-09-14 |  | 2026-09-14 |  |  | 36:27 | 485 | 200 | 41.24% |  | Cable Recieved on 04.09.26 | 2026-06-02: FALSE
RDMS00008 | 2 | 11kv Trafo.FDR. to Transformer =3cx300sqmm AL. | 15 | Mtr | Dinesh Purohit | 10 | 2026-10-09 | 2026-10-10 |  | 2026-10-10 |  |  | -24.4814 | 15 |  | 0% |  | Transformer not recived | 2026-06-02: FALSE
RDMS00009 | 2B | LT POWER Cables | [16 empty] | 2026-06-02: FALSE
RDMS00010 | 1 | Transformer to I/C PMCC =10Rx3Cx120sqmm COPPER. | 200 | Mtr | Dinesh Purohit | 10 | 2026-10-22 | 2026-10-24 |  | 2026-10-24 |  |  | 48:00 | 200 |  | 0% |  | Site Not Ready | 2026-06-02: #REF!
RDMS00011 | 2 | PMCC to 50kva Lighting Trafo. =3Cx120sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Site Not Ready | 2026-06-02: #REF!
RDMS00012 | 3 | PMCC to Battery Charger = 3Cx35sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Site Not Ready
RDMS00013 | 4 | PMCC to UPS= 3Cx10sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Site Not Ready
RDMS00014 | 5 | PMCC to NGR= 3Cx2.5sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Site Not Ready
RDMS00015 | 6 | PMCC to TRAFO MJB = 3Cx2.5sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Site Not Ready
RDMS00016 | 7 | Battery Charger to Battery Bank =3Cx120sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Not Recieved
RDMS00017 | 8 | Battery Charger to 11kv I/C Panel 24v DC =3Cx2.5sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Not Recieved
RDMS00018 | 9 | Battery Charger to NGR =3Cx2.5sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Not Recieved
RDMS00019 | 10 | UPS to UPS battery Bank =3Cx10sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Not Recieved
RDMS00020 | 11 | UPS to 11kv I/C Panel 110v AC= 3Cx2.5sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Not Recieved
RDMS00021 | 12 | 50kva Lighting Trafo. to MLDB = 4Cx16sqmm Alu | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Not Recieved
RDMS00022 | 13 | NGR to Ground= 1Cx95sqmm Cup. | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Site Not Ready
RDMS00023 | 2C | Control Cables
RDMS00024 | 2c1 | 11kv Transformer FDR to MJB = 2Rx7Cx2.5sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Site Not Ready
RDMS00025 | 2c2 | 11kv Transformer FDR to NGR =7Cx2.5sqmm | 20 | Mtr | Dinesh Purohit | 10 | 2026-10-25 | 2026-10-27 |  | 2026-10-27 |  |  | 48:00 | 20 |  | 0% |  | Site Not Ready
RDMS00026 | 3 | Design and fabrication as per HZL standard for installation of equipment |  |  | Heeralal Ji | 1 | 2026-05-01 | 2026-05-10 | 10 | 2026-05-10 |  |  | 3084:27 |  |  |  |  | Site Not Ready
RDMS00027 | 4 | Erection of sub-station
RDMS00028 | a | 2MVA Transformers: | 1 | No | Dinesh Purohit | 6 | 2026-10-07 | 2026-10-09 | 5 | 2026-10-09 |  |  | 48:00 | 1 |  | 0% |  | Item not Recieved
RDMS00029 | b | HT Switchgear: (1 Incoming 3 Outgoing) | 1 | No | Dinesh Purohit | 6 | 2026-10-07 | 2026-10-09 | 7 | 2026-10-09 |  |  | 48:00 | 1 |  | 0% |  | Building Not Complete
RDMS00030 | c | LT Switchgear:(1 Incoming 16 Outgoing) | 1 | No | Dinesh Purohit | 6 | 2026-10-10 | 2026-10-12 | 5 | 2026-10-12 |  |  | 48:00 | 1 |  | 0% |  | Building Not Complete
RDMS00031 | d | Battery Charger installation | 1 | No | Dinesh Purohit | 6 | 2026-10-13 | 2026-10-14 | 2 | 2026-10-14 |  |  | 24:00 | 1 |  | 0% |  | Item not Recieved
RDMS00032 | e | NGR installation | 1 | No | Dinesh Purohit | 6 | 2026-10-15 | 2026-10-16 | 2 | 2026-10-16 |  |  | 24:00 | 1 |  | 0% |  | Building Not Complete
RDMS00033 | f | UPS Installation | 1 | No | Dinesh Purohit | 6 | 2026-10-17 | 2026-10-19 | 2 | 2026-10-19 |  |  | 48:00 | 1 |  | 0% |  | Item not Recieved
RDMS00034 | g | 50 KVA lighting transformer erection | 1 | No | Dinesh Purohit | 6 | 2026-10-20 | 2026-10-21 | 2 | 2026-10-21 |  |  | 24:00 | 1 |  | 0% |  | Item not Recieved
RDMS00035 | h | Fire Suppression System for Dry type transformer | 2 | Nos | Dinesh Purohit | 6 | 2026-10-22 | 2026-10-24 | 2 | 2026-10-24 |  |  | 48:00 | 2 |  | 0% |  | Item not Recieved
RDMS00036 | 5 | Terminations of cables - (HT /LT/Control Terminations )
RDMS00037 | a | 2MVA Transformers: | 1 | No | Dinesh Purohit | 4 | 2026-11-01 | 2026-11-04 | 3 | 2026-11-04 |  |  | 72:00 | 1 |  | 0% |  | Building Not Complete
RDMS00038 | b | HT Switchgear: (1 Incoming 3 Outgoing) | 1 | No | Dinesh Purohit | 4 | 2026-11-05 | 2026-11-08 | 3 | 2026-11-08 |  |  | 72:00 | 1 |  | 0% |  | Building Not Complete
RDMS00039 | c | LT Switchgear:(1 Incoming 16 Outgoing) | 1 | No | Dinesh Purohit | 4 | 2026-11-09 | 2026-11-10 | 1 | 2026-11-10 |  |  | 24:00 | 1 |  | 0% |  | Building Not Complete
RDMS00040 | d | Battery Charger installation | 1 | No | Dinesh Purohit | 4 | 2026-11-11 | 2026-11-12 | 1 | 2026-11-12 |  |  | 24:00 | 1 |  | 0% |  | Item not Recieved
RDMS00041 | e | NGR installation | 1 | No | Dinesh Purohit | 4 | 2026-11-13 | 2026-11-14 | 1 | 2026-11-14 |  |  | 24:00 | 1 |  | 0% |  | Building Not Complete
RDMS00042 | f | UPS Installation | 1 | No | Dinesh Purohit | 4 | 2026-11-15 | 2026-11-16 | 1 | 2026-11-16 |  |  | 24:00 | 1 |  | 0% |  | Building Not Complete
RDMS00043 | g | 50 KVA lighting transformer erection | 1 | No | Dinesh Purohit | 4 | 2026-11-17 | 2026-11-18 | 1 | 2026-11-18 |  |  | 24:00 | 1 |  | 0% |  | Item not Recieved
RDMS00044 |  | Other Termination & lighting
RDMS00045 | h | Fire Detection System, | 1 | Nos | Dinesh Purohit | 4 | 2026-11-05 | 2026-11-16 | 11 | 2026-11-16 |  |  | 264:00 | 1 |  | 0% |  | Item not Recieved
RDMS00046 | i | SS Building lighting installation | 1 | Nos | Dinesh Purohit | 4 | 2026-11-04 | 2026-11-17 | 13 | 2026-11-17 |  |  | 312:00 | 1 |  | 0% |  | Site Not Ready
RDMS00048 | 6 | Testing of sub-station
RDMS00049 | a | For Transformers: IR Test, Ratio Test, Vector Group Test, Magnetic Balance Test, Functional Test | 1 | No | Dinesh Purohit | 6 | 2026-11-19 | 2026-11-22 | 3 | 2026-11-22 |  |  | 72:00 | 1 |  | 0% |  | Site Not Ready
RDMS00050 | b | For HT Switchgear: IR Test, Functional Test, CRM, Closing/Opening Time, Coil Resistance, Numerical Relay Test by Primary and Secondary Current Injection (1 Incoming 3 Outgoing) | 1 | No | Dinesh Purohit | 6 | 2026-11-23 | 2026-11-25 | 2 | 2026-11-25 |  |  | 48:00 | 1 |  | 0% |  | Site Not Ready
RDMS00051 | c | For LT Switchgear: IR Test, Functional Test, Numerical Relay Test by Primary and Secondary Current Injection -(1 Incoming 16 Outgoing) | 1 | No | Dinesh Purohit | 6 | 2026-11-26 | 2026-11-27 | 1 | 2026-11-27 |  |  | 24:00 | 1 |  | 0% |  | Site Not Ready
RDMS00052 | d | For Cables: IR Test | 1 | No | Dinesh Purohit | 6 | 2026-11-28 | 2026-11-29 | 1 | 2026-11-29 |  |  | 24:00 | 1 |  | 0% |  | Site Not Ready
RDMS00053 | e | For Others: Functional Test, IR Test (as applicable) | 1 | No | Dinesh Purohit | 6 | 2026-11-30 | 2026-12-01 | 1 | 2026-12-01 |  |  | 24:00 | 1 |  | 0% |  | Site Not Ready
RDMS00054 | f | Battery Charger-Testing & commissioning | 1 | No | Dinesh Purohit | 6 | 2026-12-02 | 2026-12-03 | 1 | 2026-12-03 |  |  | 24:00 | 1 |  | 0% |  | Site Not Ready
RDMS00055 | g | NGR- testing & Commissioning | 1 | No | Dinesh Purohit | 6 | 2026-12-04 | 2026-12-05 | 1 | 2026-12-05 |  |  | 24:00 | 1 |  | 0% |  | Site Not Ready
RDMS00056 | h | UPS -Testing & commiisioning | 1 | No | Dinesh Purohit | 6 | 2026-12-06 | 2026-12-07 | 1 | 2026-12-07 |  |  | 24:00 | 1 |  | 0% |  | Site Not Ready
RDMS00057 | i | 50 KVA lighting transformer- testing and Commissioning | 1 | No | Dinesh Purohit | 6 | 2026-12-08 | 2026-12-10 | 2 | 2026-12-10 |  |  | 48:00 | 1 |  | 0% |  | Site Not Ready
RDMS00058 | 7 | Installation of Earth pits with excavation | 8 | no | Dinesh Purohit | 2 | 2026-12-11 | 2026-12-13 | 2 | 2026-12-13 |  |  | 48:00 | 8 |  | 0% |  | Site Not Ready
RDMS00059 | 8 | Earting connection with earthing strips & grid- as per drawing | 8 | No | Dinesh Purohit | 6 | 2026-11-18 | 2026-11-21 | 3 | 2026-11-21 |  |  | 72:00 | 8 |  | 0% |  | Site Not Ready
RDMS00060 | 9 | Substation Charging | 1 | No | Dinesh Purohit | 6 | 2026-12-11 | 2026-12-13 | 2 | 2026-12-13 |  |  | 48:00 | 1 |  | 0% |  | Site Not Ready
RDMS00061 | 10 | Installation of Lighting arrestor - 2 mtr copper rod | 6 | no | Dinesh Purohit | 6 | 2026-12-14 | 2026-12-16 | 2 | 2026-12-16 |  |  | 48:00 | 6 |  | 0% |  | Site Not Ready
RDMS00062 | 11 | Safety and other accessories -hand over | 1 | LS | Dinesh Purohit | 6 | 2026-12-17 | 2026-12-22 | 5 | 2026-12-22 |  |  | 120:00 | 1 |  | 0% |  | Site Not Ready
RDMS00063 | 12 | Punch Points of Substation - to be cleared | 1 | LS | Dinesh Purohit | 5 | 2026-12-14 | 2026-12-24 | 10 | 2026-12-24 |  |  | 240:00 | 1 |  | 0% |  | Site Not Ready
RDMS00064 | 13 | Documentation and preparation of application file for submission to DGMS for approval. (3 copies of each file/drawings/manuals to be submitted) | 1 | LS | Dinesh Purohit | 1 | 2026-12-18 | 2026-12-25 | 7 | 2026-12-25 |  |  | 168:00 | 1 |  | 0% |  | Site Not Ready
RDMS00065 | B | Work for Re-routing power cable on Portal side
RDMS00066 | 1 | Laying of all the cable mentioned in Point no 1 on the cable alley structure of 1mtr height at distance of 1.5mtr with cable tray 750mm size and the H type - support shall be made with channel size of 100mm and angle 65mm. Also condsider the two road crossing with hume pipe arrangment. All the material, tools and tackels, hydra, cherry picker, cable stand, lifting belts , safety items and etc required for the job shall be in vendor scope. Shifting of cable drum from central store to the site shall be in vendor scope. The job include designing, erection and commissioning of cable structure in the vendor scope. structure shall be GI painted. All the excavation shall be in vendor scope | 2000 | mtr | Dinesh Purohit | [8 empty] | 2000 |  | 0%
RDMS00067 | 1a | 3Cx 185 sqmm LSZH XLPE insulated double armoured copper cable | 600 | M |  | 10 | 2026-09-07 | 2026-09-17 | 8 | 2026-09-17 |  |  | 240:00 | 600 | 300 | 50%
RDMS00068 | 1b | 11kv BBL S/S to 11mRL SS = 3X300sqmm LSZH XLPE Insulated double armoured aluminium cable | 750 | M |  | 20 | 2026-05-10 | 2026-05-15 | 5 | 2026-05-15 |  |  | 2964:27 | 750 | 500 | 66.67%
RDMS00069 | 1c | 11kv BBL S/S to 11kv East load Ventilation Fan=3X300sqmm LSZH XLPE Insulated double armoured aluminium cable | 750 | M |  | 10 | 2026-08-01 | 2026-08-06 | 5 | 2026-08-06 |  |  | 972:27 | 750 |  | 0%
RDMS00070 | 1d | 11kv BBL S/S to Compressor House=3X300sqmm LSZH XLPE Insulated double armoured aluminium cable | 750 | M |  | 10 | 2026-08-07 | 2026-08-11 | 5 | 2026-08-11 | 2026-09-09 09:55 |  | 705:55 | 750 |  | 0%
RDMS00071 | 1e | OFC cable 12 core single mode | 1000 | M |  | 10 | 2026-06-15 | 2026-06-19 | 5 | 2026-06-19 |  |  | 2124:27 | 1000 |  |  |  | Site Not Ready
RDMS00072 | 2 | Erection of cable tray 750MMX100MMX2MM with GI earthing | 2600 | mtr | [9 empty] | 2600 |  | 0%
RDMS00073 | 2a | Part-1 33 KV SS BBL to Existing cable tray route | 300 | Mtr | Dinesh Purohit | 6 | 2026-05-25 | 2026-05-27 | 6 | 2026-05-27 | 2026-08-21 16:52 | Done | 2080:52 | 300 | 300 | 100%
RDMS00074 | 2b | Part-2 Complete tray route-33 KV SS BBL to portal SS | 1000 | Mtr | Dinesh Purohit | 6 | 2026-05-19 | 2026-06-10 | 10 | 2026-06-10 | 2026-09-10 10:44 |  | 2218:44 | 1000 | 650 | 65% |  | All Work Done as per HZL
RDMS00075 | 2c | Part-3 At substaion area to existing tray connectivity | 1300 | Mtr | Dinesh Purohit | 6 | 2026-10-07 | 2026-10-13 | 10 | 2026-10-13 |  |  | 144:00 | 1300 |  | 0% |  | Not in BOQ
RDMS00076 | 3 | Cable marking of 11KV cable at every 10 meter with proper stand of 300mm height made with 25mm angle plate of 300mmX100mm weld to the cable structure | 100 | no | Dinesh Purohit | 4 | 2026-09-18 | 2026-09-24 | 6 | 2026-09-24 |  |  | 144:00 | 100 |  | 0% |  | Item Not Revieved
RDMS00077 | 4 | Installation of 11KV 3Cx185sqmm UE indoor termination kit with required copper lugs shall be in vendor scope | 3 | NO | Dinesh Purohit | 4 | 2026-11-01 | 2026-11-05 | 4 | 2026-11-05 |  |  | 96:00 | 3 |  | 0% |  | Site Not Ready
RDMS00078 | 5 | Installation of 11KV 3Cx185sqmm UE indoor straight through with required copper in line connector shall be in vendor scope | 4 | NO | Dinesh Purohit | 4 | 2026-11-06 | 2026-09-08 | 3 | 2026-09-08 |  |  |  | 4 |  | 0% |  | Site Not Ready
RDMS00079 | 6 | Installation of 11KV 3Cx300sqmm UE indoor termination kit with required copper lugs shall be in vendor scope | 4 | no | Dinesh Purohit | 6 | 2026-11-10 | 2026-11-14 | 4 | 2026-11-14 |  |  | 96:00 | 4 |  | 0% |  | Site Not Ready
RDMS00080 | 7 | Installation of 11KV 3Cx300sqmm UE indoor straight through with required copper in line connector shall be in vendor scope | 10 | NO | Dinesh Purohit | 6 | 2026-11-15 | 2026-11-22 | 7 | 2026-11-22 |  |  | 168:00 | 10 |  | 0% |  | Site Not Ready
RDMS00081 | 8 | Fabrication of MS for additional Cable Structure if required | 5 | MT | Dinesh Purohit | 6 | 2026-05-16 | 2026-06-10 | 25 | 2026-06-10 | 2026-09-10 10:52 | Done | 2218:52 | 5 | 5 | 100%
RDMS00082 | 9 | Disconnection of existing cable. HZL Shall give required isolation. (Vendor shall bring two cable jointer so that time taken for jointing shall be less. Insulation meggar for checking the cable shall be in vendor scope) | 4 | NO | Dinesh Purohit | 6 | 2026-05-31 | 2026-06-09 | 10 | 2026-06-09 |  |  | 2364:27 | 4 | 2 | 50%
RDMS00083 | 10 | Complete shifting of electrical swicthgears from Surface store to site in surface. (All necessary arrangement of Hydra/crane, truck tolls and tackles) | 4 | no | Dinesh Purohit | 6 | 2026-06-09 | 2026-06-16 | 5 | 2026-06-16 |  |  | 2196:27 | 4 |  | 0% |  | Site Not Ready
RDMS00084 | 11 | OFC Splicing and -network establishement | 10 | NO | Dinesh Purohit | 3 | 2026-06-25 | 2026-06-27 | 2 | 2026-06-27 |  |  | 1932:27 | 10 |  | 0% |  | Site Not Ready
RDMS00085 |  | Surface Portal Civil Building Works
RDMS00086 | A1 | SECTION 1-1 TRENCH WALL SHUTTERING AND BEAM SHUTTERING | 1 | Nos | Dinesh Purohit | 1 | 2026-07-12 | 2026-07-13 | 1 | 2026-07-13 | 2026-08-21 16:53 | Done | 952:53 | 1 | 1 | 100%
RDMS00087 | A2 | SECTION 1-1 WLL CASTING & SECTION 2-2 WALL SHUTTERING | 1 | Nos | Dinesh Purohit | 1 | 13-07-2026 | 2026-07-14 | 1 | 2026-07-14 | 2026-08-21 16:54 | Done | 928:54 | 1 | 1 | 100%
RDMS00088 | A3 | BEAM CASTING & SECTION 2-2 WALL CASTING | 1 |  | Dinesh Purohit | 1 | 14-07-2026 | 2026-07-15 | 1 | 2026-07-15 | 2026-08-21 16:54 | Done | 904:54 | 1 | 1 | 100%
RDMS00089 | A4 | SECTION 3-3 WALL SHUTTERING & BEAM STEEL BINDING | 1 |  | Dinesh Purohit | 1 | 2026-07-15 | 2026-07-16 | 1 | 2026-07-16 | 2026-08-21 16:54 | Done | 880:54 | 1 | 1 | 100%
RDMS00090 | A5 | COLUMN SHUTTERING C3-C4-C5-C6 & WALL CASTING SECTION 3-3 & BEAM CASTING | 0.5 |  | Dinesh Purohit | 1 | 16-07-2026 | 2026-07-18 | 2 | 2026-07-18 | 2026-08-21 16:54 | Done | 832:54 | 0.5 | 0.5 | 100%
RDMS00091 | A6 | BRICK MASONRY & COLUMN C8-C10-C14-C13 & BACK FILLING | 0.5 |  | Dinesh Purohit | 1 | 18-07-2026 | 2026-07-20 | 2 | 2026-07-20 | 2026-08-21 16:54 | Done | 784:54 | 0.5 | 0.5 | 100%
RDMS00092 | A7 | BRICK MASONRY & COLUMN C12-C11-C9-C7 & COMPECTION & SOILING |  |  | Dinesh Purohit | 1 | 20-07-2026 | 2026-07-21 | 1 | 2026-07-21 | 2026-08-21 16:54 | Done | 760:54 |  |  | 100%
RDMS00093 | A8 | BRICK WORK & CHAJJA CASTING & FLOOR PCC WORK |  |  | Dinesh Purohit | 1 | 21-07-2026 | 2026-07-22 | 1 | 2026-07-22 | 2026-08-21 16:54 | Done | 736:54 |  |  | 100%
RDMS00094 | A9 | BRICK MASONRY & SLAB BOTTAM WORK |  |  | Dinesh Purohit | 1 | 22-07-2026 | 2026-07-25 | 3 | 2026-07-25 | 2026-08-21 16:54 | Done | 664:54 |  |  | 100%
RDMS00095 | A10 | SCAFFOLDING & BRICK MASONRY & SLAB BOTTAM WORK |  |  | Dinesh Purohit | 1 | 25-07-2026 | 2026-07-27 | 2 | 2026-07-27 | 2026-09-03 15:26 | Done | 927:25 |  |  | 100%
RDMS00096 | A11 | SCAFFOLDING WORK SLAB WORK |  |  | Dinesh Purohit | 1 | 27-07-2026 | 2026-07-30 | 3 | 2026-07-30 | 2026-09-04 11:23 | Done | 875:23 |  |  | 100%
RDMS00097 | A12 | STEEL BINDING WORK FOR SLAB & BEAM |  |  | Dinesh Purohit | 1 | 30-07-2026 | 2026-02-08 | 2 | 2026-02-08 | 2026-09-08 11:00 | Done | 5099:00 |  |  | 100%
RDMS00098 | A13 | SLAB CASTING |  |  | Dinesh Purohit | 1 | 2026-02-08 | 2026-05-08 | 3 | 2026-05-08 | 2026-09-08 11:00 | Done | 2963:00 |  |  | 100%
RDMS00099 | A14 | OUTER SIDE PLASTER & PERAPIT WALL |  |  | Dinesh Purohit | 1 | 2026-09-08 | 2026-09-13 | 5 | 2026-09-13 | 2026-09-09 09:50 |  |  |  |  | 20%
RDMS00100 | A15 | OUTER SDE PLASTER AND TRANSFORMER FOUNDATION WORK |  |  | Dinesh Purohit | 1 | 09-14-2026 | 2026-09-18 | 4 | 2026-09-18 | 2026-09-09 09:48 |  |  |  |  | 20%
RDMS00101 | A16 | SLAB SCREEDING WORK |  |  | Dinesh Purohit | 1 | 2026-09-19 | 2026-09-20 | 1 | 2026-09-20 |  |  | -4.4814
RDMS00102 | A17 | SLAB DESHUTTERING |  |  | Dinesh Purohit | 1 | 2026-09-07 | 2026-10-05 | 28 | 2026-10-05 |  |  | -19.4814
| Note : | PMS is subjected to all resorces availability / fullkitting
| 1 | Supply material availability
| 2 | Civil Building availability
| 3 | Manpower availability
| 4 | Cable jointer availability